# Quality Management System (QMS)

# Implementation Project Plan

| Project plan approved by |  |
| --- | --- |
| Approved date |  |

Instructions:

- Review and amend content to ensure it reflects your organisation’s requirements and plans. Note examples have been included in some tables, these should be adjusted and expanded on depending on your organisation’s needs

- Update table of contents as required

- Obtain approval (generally this would be by the CEO or equivalent)

- Delete these instructions

Contents

Objectives	3

Deliverables	3

Milestones	4

Action plan	4

Project team	6

Staff engagement and communication plan	7

Resourcing plan	9

Risk Management	10

Required Reading plan	11

Project review	12

## Objectives

e.g.:

- To implement a new quality management system for operational use that contains up-to-date policies, processes and documents that align with the new Aged Care Act, strengthened Aged Care Quality Standards and other key legislative requirements.

- To consolidate existing policy, process and template tools and resources used by our organisation into a single portal for use by all applicable staff.

- To implement a portal that allows our organisation to move away from a paper-based system for reporting of incidents, complaints and feedback.

## Deliverables

e.g.:

- All policies and processes aligned to the Aged Care Quality & Safety Standards.

- Agreement/development of a Policy Management Framework (you may wish to adapt the QMS Management Framework Template for your purposes).

- All applicable internally created policy, process and template documents added to the QMS.

- Up-to-date policies, processes and documents are personalised to our organisation, available on the system and named consistently and logically.

- Configuration of the system (refer to QMS Configuration Guide for more information).

- All staff are knowledgeable of the requirements of the Standards and trained on changes in work practices.

- All staff have access to the QMS, have received training on the system and know how to navigate the system to access policies, processes and documents.

- All staff using the Registers system to report incidents, feedback and complaints related to service provision and work health and safety.

- Have a regular auditing program in place to test operational practice against requirements.

- All older people and their supporters (i.e. families, carers and decision-makers) are aware of the new quality standards.

## Milestones

## Action plan

| Activity | Responsible Role | Due date |
| --- | --- | --- |
| Plan |  |  |
| Review update and approve Project Plan. |  |  |
| Assign project team and ensure all those named are aware of their responsibilities |  |  |
| Confirm modules and components of QMS which will be utilised and when (i.e. Required Reading, specific content suites, Registers, Audits) |  |  |
| Establish system and project governance (e.g. policy management committee) |  |  |
| Create meeting schedule for project team (and/or policy management committee) and invite all members |  |  |
| Identify key dates (e.g. reporting, completion of key activities, communications to staff, training etc) |  |  |
| Develop staff engagement plan and consider other stakeholder communications including other system users, older people and their supporters etc. |  |  |
| Finalise Policy Framework (e.g. using the QMS Management Framework Template) including agreement on a naming/coding model and system administrator responsibilities |  |  |
| Develop communication and training plan for staff |  |  |
| Schedule communications and training |  |  |
| Determine parameters for staff (including associated provider staff) access to QMS (i.e. physical assets required on site for access, remote worker internet access, etc) |  |  |
| Personalise |  |  |
| Schedule administrator training for key QMS administrators (e.g. initial onboarding for all key decision-makers plus additional training for administrators) |  |  |
| Map current internal policies, processes and documents. Determine what will be archived, added to QMS, merged, etc |  |  |
| Review QMS content and identify which policies, processes and documents will be kept as is, updated or archived (hidden) |  |  |
| Update current policies, processes and documents as identified |  |  |
| Upload internal content to QMS |  |  |
| Configure QMS settings (e.g. Roles, Business Units, Required Reading) |  |  |
| Set up audit schedule (i.e. for first 6 months) |  |  |
| Create Required Reading plan for staff roles |  |  |
| Implement |  |  |
| Initiate communication plan with all staff |  |  |
| Add all users (e.g. using the Bulk User Upload Template) |  |  |
| Train all staff users including task specific training as required e.g. use of Registers, completing Audits, Required Reading etc. (e.g. using the QMS User Training Template) |  |  |
| Close down/archive superseded content and/or systems |  |  |
| Evaluate system implementation including by seeking feedback from users about their experience |  |  |
| Update and review content within QMS as required (i.e. regular internal review and QMS updates) |  |  |

## Project team

| Name | Role | Responsibilities |
| --- | --- | --- |
| [insert name of person responsible] | Executive Sponsor | Promote the change of system and work practices including communicating why it’s happening and risks if isn’t done directly to staff Be accessible to staff and invite feedback Ensure resources are available to complete the project Provide guidance to the Project Team |
| [insert name of person responsible] | Project and Change Lead | Manage the work to ensure the activities are completed by the agreed time and staff are supported to adopt the changes Provide progress reports |
| [insert name of person responsible] | Project Team member | Complete designated activities within agreed timeframes |
| [insert name of person responsible] | Project Team member | Complete designated activities within agreed timeframes |
| [insert name of person responsible] | Project Team member | Complete designated activities within agreed timeframes |

## Staff engagement and communication plan

| Format/event | Message | Responsibility | Due date |
| --- | --- | --- | --- |
| Phase 1: Preparing for the change |  |  |  |
| All staff/team meetings | What is and isn’t changing Why it is needed (i.e. purpose, benefits for the business and impact if it’s not done) How staff jobs will be improved How the change aligns with their priorities/strategic plan Details of project activities and timelines How staff can be involved How they will be supported through the change Timelines for the change |  |  |
| Newsletters/Notice boards |  |  |  |
| All staff emails |  |  |  |
| Ad hoc discussions |  |  |  |
| Phase 2: Implementing the change |  |  |  |
| All staff/team meetings | Restate what’s changing and why Update progress and next steps Inform on changed ways of working Inform of training plan Inform of support options (i.e. QMS Support Portal resources, where to go for help) Provide details of process to login to QMS (i.e. invite email, setting password) |  |  |
| Newsletters/Notice boards |  |  |  |
| All staff emails |  |  |  |
| Staff training | Restate what’s changing and why Inform on changed ways of working Provide details of process to login to QMS (i.e. invite email, setting password) Inform of support options (i.e. QMS Support Portal resources, where to go for help) |  |  |
| Individual staff discussions | Changes to their specific roles Expected performance and behaviour changes What’s in it for them Any trade-offs or downsides of the change |  |  |
| Management meetings | Restate what’s changing and why Update progress and next steps Impact on teams and service delivery Risk identification and management Identification of areas of resistance and management strategies |  |  |
| Board meetings | Progress reporting Risk mitigation strategies |  |  |
| Phase 3: Reinforcing the change |  |  |  |
| All staff/team meeting | Restate importance of new systems and processes Inform on new ways of working Inform of support options (i.e. training, QMS Support Portal resources, where to go for help) |  |  |
| Newsletters/Notice boards |  |  |  |
| All staff emails |  |  |  |
| Individual staff discussions | Support to adopt changes when non-compliance identified Expected performance and behaviour changes |  |  |
| Leadership meetings | Outcomes of adoption reporting Strategies to manage resistance |  |  |

## Resourcing plan

| Resource | Reason | Resource type | Parameters | Budget | Due date |
| --- | --- | --- | --- | --- | --- |
| e.g. Project team members | To coordinate roll out of new system and change management. Meet approx. weekly with various tasks assigned. | Human resource | Approx. XX EFT | $XX |  |
| e.g. QMS Administrator | To action personalisation and configuration of the QMS | Human resource | Approx. XX weeks work required | $XX |  |
| e.g. Training room | To facilitate staff training | Physical | e.g. Space for XX Staff required | $XX |  |
| e.g. Internet access and computers/tablets | To allow staff access to QMS resources | Physical & IT | e.g. On-site computer required for office space | $XX |  |

## Risk Management

i.e. risks related to this implementation plan

| Risk | Details/Impact | Control | Responsibility |
| --- | --- | --- | --- |
| e.g. Staff do not access QMS, poor digital literacy | e.g. Staff not following policy/process may result in poor quality care and/or non-compliant care | e.g. provide IT infrastructure to all staff, staff training, reminders in meetings, etc | e.g. IT & HR team |
| e.g. content updates not integrated promptly or personalised | e.g. compliance risk as content may not be aligned with changing industry needs, content may not reflect current operations or organisational structure | e.g. dedicated resource responsible for ongoing updating, update contact details with Ageing Australia for key administrators, set up internal review schedule, etc | e.g. quality team |
| e.g. staff not completing Required Reading | e.g. evidence that staff are not aware of or following policy/process | e.g. send reports regularly to managers, set up Required Reading reminder alerts through QMS. | e.g. leadership team |

## Required Reading plan

| Role name (QMS) | Purpose | Job types included | Required Reading items | Timelines |
| --- | --- | --- | --- | --- |
| e.g. Onboarding | e.g. To assign RR for all staff, including new staff of essential content items | e.g. All staff roles at all levels | e.g. Abuse prevention and response content Incident reporting content Feedback and complaints content Whistleblowing content | e.g. To be assigned at initial deployment for all staff for completion within first 2 months. |
| e.g. Care Worker | e.g. To assign care worker specific content for non-clinical staff | e.g. All non-clinical care staff including personal care workers and those providing domestic assistance, social support or other care services | e.g. Personal care provision process, Dignity and choice content, etc | e.g. to be assigned following initial reading for completion in 1 month |
| e.g. Clinical staff | e.g. to assign essential clinical care content to applicable workers | e.g. management staff, all clinical care staff incl. registered nurses and enrolled nurses | e.g. Clinical Care policy, specialised nursing care policy and all related processes | e.g. to be assigned following initial reading for completion in 1 month |

## Project review

| Review activity | Details | Responsibility | Due date |
| --- | --- | --- | --- |
| e.g. Review currency of content | e.g. frequency, when will it start, what will be involved, how will it be reported? | e.g. Quality team members |  |
| e.g. Staff survey | e.g. frequency, what questions will be asked, how will it be reported? | e.g. HR team |  |
| e.g. Required Reading Reports | e.g. generate Required Reading reports monthly/quarterly to share with leadership team | e.g. system administrator |  |